## Gantt Chart
PROJECT: THE SAGE BY REPOSE — CONSTRUCTION PLANNING | [7 empty] | OVERALL PROGRESS |  |  |  |  | 50.73%
START DATE: Oct 2024 ¦ END DATE: DEC 2027 ¦ PROJECT DURATION: ~3 Years | [7 empty] | PROJECT TIMELINE
[6 empty] | MONTHS PASSED(31ST MAY,26) | ACTUAL (%) COMPLETE | 2024 |  |  | 2025 | [11 empty] | 2026 | [11 empty] | 2027
TASK NO. | TASK NAME | START DATE | PLANNED END DATE | END DATE | DURATION(in days) |  |  | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | Remarks
1 | MAIN GATE(INC. STRUCTURE) | NA | Completed |  | 0 |  | 100%
2 | MATERIAL GATE | NA | Completed |  | 0 |  | 100%
3 | PLOT BOUNDRY WALL | NA | Completed |  | 0 |  | 100%
1.0 SOUTH GREENWAY-1 | [6 empty] | 100%
1.1 | Civil work | 11-Dec-24 | Completed |  | 0 |  | 100%
1.2 | MEP work | 08-Jan-25 | Completed |  | 0 |  | 100%
1.3 | Finishing Work | 20-Jan-25 | Completed |  | 0 |  | 100%
1.4 | lighting work | 20-Jan-25 | Completed |  | 0 |  | 100%
1.5 | Landscape work | 25-Jan-25 | Completed |  | 0 |  | 100%
2.0 SOUTH GREENWAY -2 |  |  |  |  | 10MONTHS | 3.5333 | 60%
2.1 | Civil work | 2026-02-15 | 2026-05-15 | 2026-09-30 | 227 | MONTHS | 80% | [16 empty] | 80% | [6 empty] | 80%
2.2 | MEP work(PRE) | 2026-06-15 | 2026-10-31 | 2026-06-25 | 10 |  | 100% | [20 empty] | 100%
2.3 | Finishing Work | 2026-06-16 | 2026-10-31 | 2026-11-30 | 167 |  | 0% | [21 empty] | 0% | [17 empty] | Finishing contractor required
| MEP Work(post) | 2026-11-13 |  | 2026-11-30 | 17 |  | 0% | [25 empty] | 0%
2.4 | lighting work | 2026-10-30 | 2026-10-15 | 2026-11-30 | 31 |  | 0% | [24 empty] | 0%
2.5 | Landscape work | 2026-11-15 | 2026-10-31 | 2027-01-15 | 61 |  | 0% | [23 empty] | 0% |  |  | 0% | 0%
3.0 SOUTH GREENWAY-3 |  |  |  |  | 10MONTHS | 3.1333 | 33.33%
3.1 | Civil work | 2026-02-27 | 2026-05-30 | 2026-09-30 | 215 | MONTHS | 60% | [17 empty] | 60% | [5 empty] | 60%
3.2 | MEP work(PRE) | 2026-06-30 | 2026-10-31 | 2026-07-10 | 10 |  | 40% | [21 empty] | 40%
3.3 | Finishing Work | 2026-07-01 | 2026-10-31 | 2026-12-15 | 167 |  | 0% | [21 empty] | 0% | [17 empty] | Finishing contractor required
| MEP Work(post) | 2026-12-01 |  | 2026-12-11 | 10 |  | 0% | [26 empty] | 0%
3.4 | lighting work | 2026-11-15 | 2026-10-15 | 2026-12-15 | 30 |  | 0% | [26 empty] | 0%
3.5 | Landscape work | 2026-09-25 | 2026-10-31 | 2026-11-25 | 61 |  | 0% | [24 empty] | 0%
4.0 SOUTH GREENWAY-4 |  |  |  |  | 11MONTHS | 3.5333 | 36.67%
4.1 | Civil work | 2026-02-15 | 2026-06-30 | 2026-09-30 | 227 | MONTHS | 60% | [16 empty] | 60% | [6 empty] | 60%
4.2 | MEP work(PRE) | 2026-07-15 | 2026-12-31 | 2026-07-25 | 10 |  | 50% | [21 empty] | 50%
4.3 | Finishing Work | 2026-06-30 | 2026-12-31 | 2026-12-31 | 184 |  | 0% | [21 empty] | 0%
| MEP Work(post) | 2026-11-20 |  | 2026-11-30 | 10 |  | 0%
4.4 | lighting work | 2026-11-15 | 2026-10-15 | 2026-12-15 | 30 |  | 0% | [26 empty] | 0%
4.5 | Landscape work | 2026-09-25 | 2026-10-31 | 2026-11-25 | 61 |  | 0% | [24 empty] | 0%
5.0 SOUTH GREENWAY-5 |  |  |  |  | 10MONTHS | 0.9 | 16.67%
5.1 | Civil work | 2026-05-05 | 2026-09-05 | 2026-10-15 | 163 | MONTHS | 50% | [19 empty] | 50%
5.2 | MEP work(PRE) | 2026-07-15 | 2026-12-31 | 2026-07-25 | 10 |  | 0% | [21 empty] | 0%
5.3 | Finishing Work | 2026-08-20 | 2026-12-31 | 2027-01-31 | 164 |  | 0% | [23 empty] | 0%
| MEP Work(post) | 2026-12-31 |  | 2027-01-10 | 10 |  | 0% | [27 empty] | 0%
5.4 | lighting work | 2027-01-01 | 2026-12-15 | 2027-01-31 | 30 |  | 0% | [27 empty] | 0%
5.5 | Landscape work | 2026-11-15 | 2026-12-31 | 2027-01-15 | 61 |  | 0% | [25 empty] | 0%
6.0 NORTH GREENWAY-1 |  |  |  |  | 12MONTHS | 7.6333 | 76.67%
6.1 | Civil work | 2025-10-15 | 2026-02-28 | 2026-07-31 | 289 | MONTHS | 90% | [12 empty] | 90%
6.2 | MEP work(PRE) | 2026-04-01 | 2026-08-15 | 2026-04-11 | 10 |  | 70% | [18 empty] | 70%
6.3 | Finishing Work | 2026-04-20 | 2026-08-15 | 2026-09-30 | 163 |  | 40% | [18 empty] | 40%
| MEP Work(post) | 2026-09-15 |  | 2026-09-25 | 10 |  | 0% | [23 empty] | 0%
6.4 | lighting work | 2026-08-30 | 2026-07-30 | 2026-09-30 | 31 |  | 0% | [23 empty] | 0%
6.5 | Landscape work | 2026-07-11 | 2026-08-15 | 2026-09-10 | 61 |  | 30% | [21 empty] | 30%
7.0 NORTH GREENWAY-2 |  |  |  |  | 8MONTHS | 0.033333 | 6.667%
7.1 | Civil work | 2026-05-31 | 2026-08-31 | 2026-10-30 | 152 | MONTHS | 20% | [20 empty] | 20%
7.2 | MEP work(PRE) | 2026-08-01 | 2026-12-31 | 2026-08-11 | 10 |  | 0% | [22 empty] | 0%
7.3 | Finishing Work | 2026-07-15 | 2026-12-31 | 2026-12-31 | 169 |  | 0% | [22 empty] | 0%
| MEP Work(post) | 2026-12-15 |  | 2026-12-25 | 10 |  | 0% | [26 empty] | 0%
7.4 | lighting work | 2026-12-01 | 2026-12-15 | 2026-12-31 | 30 |  | 0% | [26 empty] | 0%
7.5 | Landscape work | 2026-10-10 | 2026-12-31 | 2026-12-10 | 61 |  | 0% | [25 empty] | 0%
8.0 NORTH GREENWAY-3 |  |  |  |  | 6MONTHS | -3.5333 | 0%
8.1 | Civil work | 2026-09-15 | 2027-01-15 | 2027-01-15 | 122 | MONTHS | 0% | [23 empty] | 0% | [15 empty] | Work was not allotted New contractor just finalised
8.2 | MEP work(PRE) | 2026-12-01 | 2027-01-10 | 2026-12-11 | 10 |  | 0% | [26 empty] | 0%
8.3 | Finishing Work | 2026-11-15 | 2026-12-31 | 2027-04-24 | 160 |  | 0% | [25 empty] | 0%
| MEP Work(post) | 2027-04-10 |  | 2027-04-20 | 10 |  | 0% | [30 empty] | 0%
8.4 | lighting work | 2027-04-01 | 2026-12-15 | 2027-05-01 | 30 |  | 0% | [30 empty] | 0%
8.5 | Landscape work | 2026-10-31 | 2027-02-28 | 2027-03-16 | 136 |  | 0% | [25 empty] | 0%
9.0 NORTH GREENWAY-4 |  |  |  |  | 6MONTHS | -4.0667 | 0%
9.1 | Civil work | 2026-10-01 | 2027-01-31 | 2027-01-31 | 122 | MONTHS | 0% | [24 empty] | 0% | [14 empty] | Work was not allotted New contractor just finalised
9.2 | MEP work(PRE) | 2026-12-16 | 2026-12-31 | 2026-12-26 | 10 |  | 0% | [26 empty] | 0%
9.3 | Finishing Work | 2026-11-01 | 2026-12-31 | 2027-04-10 | 160 |  | 0% | [25 empty] | 0%
| MEP Work(post) | 2027-03-25 |  | 2027-04-04 | 10 |  | 0% | [30 empty] | 0%
9.4 | lighting work | 2026-11-14 | 2026-12-15 | 2026-12-15 | 31 |  | 0% | [25 empty] | 0%
9.5 | Landscape work | 2026-10-31 | 2027-03-18 | 2027-03-18 | 138 |  | 0% | [25 empty] | 0%
10.0 NORTH GREENWAY-5 |  |  |  |  | 8MONTHS | 0.56667 | 13.33%
10.1 | Civil work | 2026-05-15 | 2026-08-30 | 2026-10-10 | 148 | MONTHS | 40% | [19 empty] | 40%
10.2 | MEP work(PRE) | 2026-07-30 | 2026-12-31 | 2026-08-10 | 11 |  | 0% | [22 empty] | 0%
10.3 | Finishing Work | 2026-07-20 | 2026-12-31 | 2026-12-30 | 163 |  | 0% | [22 empty] | 0%
| MEP Work(post) | 2026-10-20 |  | 2026-10-30 | 10 |  | 0% | [24 empty] | 0%
10.4 | lighting work | 2026-11-30 | 2026-12-15 | 2026-12-30 | 30 |  | 0% | [26 empty] | 0%
10.5 | Landscape work | 2026-10-10 | 2026-12-31 | 2026-12-10 | 61 |  | 0% | [25 empty] | 0%
11.0 RECREATION LOUNGE |  |  |  |  | 27MONTHS | 20.1333 | 30%
11.1 | Civil work | 2024-10-05 | 2026-09-15 | 2026-09-15 | 710 | MONTHS | 70% | 70%
11.2 | MEP work | 2026-06-16 | 2026-12-31 | 2026-11-30 | 167 |  | 20% | [20 empty] | 20%
11.3 | Finishing work | 2026-08-01 | 2026-12-31 | 2026-12-15 | 136 |  | 0% | [22 empty] | 0%
11.4 | Interior Work | 2026-10-16 | 2026-12-31 | 2027-01-15 | 91 |  | 0% | [25 empty] | 0%
11.5 | Landscape work | 2026-07-16 | 2026-12-31 | 2026-10-15 | 91 |  | 0% | [22 empty] | 0%
11.6 | lighting work | 2026-11-16 | 2026-12-31 | 2027-01-15 | 60 |  | 0% | [25 empty] | 0%
12.0 CLUB HOUSE |  |  |  |  | 23MONTHS | 3.5333 | 10%
12.1 | Civil work | 2026-02-15 | 2026-11-29 | 2026-11-29 | 287 | MONTHS | 30% | [16 empty] | 30%
12.2 | MEP work | 2026-08-01 | 2027-12-15 | 2027-12-15 | 501 |  | 0% | [22 empty] | 0%
12.3 | Finishing work | 2026-12-01 | 2027-12-31 | 2027-12-31 | 395 |  | 0% | [26 empty] | 0%
12.4 | Interior Work | 2027-07-01 | 2027-12-31 | 2027-12-31 | 183 |  | 0% | [33 empty] | 0%
12.5 | Landscape work | 2027-10-01 | 2027-12-31 | 2027-12-31 | 91 |  | 0% | [36 empty] | 0%
12.6 | lighting work | 2027-10-01 | 2027-12-15 | 2027-12-15 | 75 |  | 0% | [36 empty] | 0%
13 | COMMON AREA LANDSCAPING DEVELOPMENT | 2024-12-15 | 2026-11-30 | 2026-11-30 | 24MONTHS | 17.7667 | 70% |  |  | 70%
14 | PLUMBING WORKS & IRRIGATION WORK | 2026-02-24 | 2026-10-30 | 2026-10-30 | 9MONTHS | 3.2333 | 90% | [17 empty] | 90%
15 | ELECTRIC WORKS | 2026-04-24 | 2026-12-30 | 2026-12-30 | 9MONTHS | 1.2667 | 50% | [19 empty] | 50%
16 | INTERNAL ROADS WITH TRIMIX | 2025-02-06 | 2027-12-31 | 2027-12-31 | 36MONTHS | 16 | 50% |  |  |  |  | 50%
NOTE:PARTIAL MONTHS ARE ROUNDED TO THE CORRESPONDING MONTH CELL;REFER TO START AND END DATES FOR EXACT DURATIONS. | [7 empty] | PHASE PROGRESS(%)
[8 empty] | Boundary & Gates |  |  |  | 100%
[8 empty] | South Greenways |  |  |  | 49.33%
[8 empty] | North Greenways |  |  |  | 19.33%
[8 empty] | Recreation/Club |  |  |  | 20%
STATUS SUMMARY | [7 empty] | Other Infrastructure |  |  |  | 65%
Total Main Tasks |  | 19
Completed (100%) |  | 4
In Progress |  | 13
Not Started (0%) |  | 2