## villa stage wise status
2026-08-30
The Sage By Repose
| Villa Progress Report |  |  |  | Start Date |  | Possession Date |  | Actual time to delivery (months) | Over all Work % as on date |  | Time to delivery (months) | Stage 1 |  | Stage2 |  | Stage 3 |  | Doors, Windows & Cobble Order placed | Doors, Windows & Cobble received | Stage 4
Sr. No | Villa No. | Villa type | Contractor | Customer Signature Date | Committed | Actual | Committed | Actual |  | Committed | Actual |  | Committed | Actual | Committed | Actual | Committed | Actual |  |  | Committed | Actual | QC + CRM inspection | CRM handover | 10th July | 20th July | 30th July | 2026-08-10 | 2026-08-20 | 2026-08-30 | 2026-09-10 | 2026-09-20 | 2026-09-30 | 2026-10-10 | 2026-10-20 | 2026-10-30
1 | N10 | 216 SQ YD | Real Infra | 2025-01-20 | 2025-02-15 | 2025-04-18 | 2026-02-14 | 2026-07-31 | 15.6333 | 100% | 95% | -1 | COMPLETE |  | COMPLETE |  | COMPLETE |  |  |  | 2026-07-01 |  | 2026-07-16 | 2026-07-26 | 95% | 95% | 95% | 2026-08-10: 95%; 2026-08-20: 95%; 2026-08-30: 95%
2 | N62 | 216 SQ YD | Real Infra | 2025-02-06 | 2025-03-15 | 2025-04-17 | 2026-03-14 | 2026-10-11 | 18.0667 | 100% | 85% | 1.4 | COMPLETE |  | COMPLETE |  | COMPLETE |  |  |  | 2026-09-11 |  | 2026-09-26 | 2026-10-06 | 80% | 85% | 85% | 2026-08-10: 85%; 2026-08-20: 85%; 2026-08-30: 85%
3 | N05 | 216 SQ YD | Real Infra | 2025-01-22 | 2025-02-24 | 2025-04-15 | 2026-02-23 | 2026-08-31 | 16.7667 | 100% | 92% | 0.033333 | COMPLETE |  | COMPLETE |  | COMPLETE |  | 2026-06-10 | 2026-07-01 | 2026-07-31 |  | 2026-08-15 | 2026-08-25 | 92% | 92% | 92% | 2026-08-10: 92%; 2026-08-20: 92%; 2026-08-30: 92%
4 | S18 | 163 SQ YD | AVS | 2025-01-24 | 2025-02-24 | 2025-05-15 | 2026-02-23 | 2026-09-30 | 16.7667 | 100% | 90% | 1.0333 | COMPLETE |  | COMPLETE |  | COMPLETE |  | 2026-07-11 | 2026-08-01 | 2026-08-31 |  | 2026-09-15 | 2026-09-25 | 90% | 90% | 90% | 2026-08-10: 90%; 2026-08-20: 90%; 2026-08-30: 90%
5 | S14 | 351 SQ YD | AVS | 2025-04-30 | 2025-06-06 | 2025-06-06 | 2026-06-05 | 2026-10-15 | 16.5333 | 100% | 85% | 1.5333 | COMPLETE |  | COMPLETE |  | COMPLETE |  | 2026-07-26 | 2026-08-16 | 2026-09-15 |  | 2026-09-30 | 2026-10-10 | 85% | 85% | 85% | 2026-08-10: 85%; 2026-08-20: 85%; 2026-08-30: 85%
6 | N27 | 216 SQ YD | Real Infra | 2025-04-22 | 2025-05-24 | 2025-05-20 | 2026-05-23 | 2026-10-30 | 17.6 | 100% | 60% | 2.0333 | COMPLETE |  | COMPLETE |  | 2026-08-30 |  | 2026-08-10 | 2026-08-31 | 2026-09-30 |  | 2026-10-15 | 2026-10-25 | 60% | 60% | 60% | 2026-08-10: 60%; 2026-08-20: 60%; 2026-08-30: 60%
7 | N14 | 216 SQ YD | Real infra | 2025-06-21 | 2025-07-24 | 2025-11-12 | 2026-07-23 | 2026-11-30 | 12.7667 | 100% | 50% | 3.0667 | COMPLETE |  | 2026-07-05 | 2026-08-29 | 2026-08-05 |  | 2026-09-10 | 2026-10-01 | 2026-10-31 |  | 2026-11-15 | 2026-11-25 | 45% | 45% | 45% | 2026-08-10: 45%; 2026-08-20: 45%; 2026-08-30: 50%
8 | N3A | 421 SQ YD | Real Infra | 2025-03-19 | 2025-04-06 | 2025-05-20 | 2026-04-05 | 2026-11-30 | 18.6333 | 100% | 60% | 3.0667 | COMPLETE |  | 2026-08-04 |  | 2026-08-30 |  | 2026-08-27 | 2026-09-17 | 2026-10-17 |  | 2026-11-01 | 2026-11-11 | 60% | 60% | 60% | 2026-08-10: 60%; 2026-08-20: 60%; 2026-08-30: 60%
9 | N09 | 480 SQ YD | Real Infra | 2025-07-09 | 2025-08-24 | 2025-11-18 | 2026-08-23 | 2026-12-31 | 13.6 | 95% | 45% | 4.1 | COMPLETE |  | 2026-08-25 |  | 2026-10-11 |  | 2026-10-10 | 2026-10-31 | 2026-11-30 |  | 2026-12-15 | 2026-12-25 | 40% | 40% | 40% | 2026-08-10: 40%; 2026-08-20: 45%; 2026-08-30: 45%
10 | S30 | 351 SQ YD | AVS | 2025-05-22 | 2025-06-15 | 2025-06-09 | 2026-06-14 | 2026-12-31 | 19 | 100% | 75% | 4.1 | COMPLETE |  | COMPLETE |  | COMPLETE |  | 2026-10-11 | 2026-11-01 | 2026-12-01 |  | 2026-12-16 | 2026-12-26 | 75% | 75% | 75% | 2026-08-10: 75%; 2026-08-20: 75%; 2026-08-30: 75%
1 | S37 | 285 SQ YD | AVS | 2025-06-11 | 2025-06-24 | 2025-11-23 | 2026-06-23 | 2027-02-15 | 14.9667 | 100% | 50% | 5.6333 | COMPLETE |  | COMPLETE |  | 2026-08-31 |  | 2026-11-26 | 2026-12-17 | 2027-01-16 |  | 2027-01-31 | 2027-02-10 | 50% | 50% | 50% | 2026-08-10: 50%; 2026-08-20: 50%; 2026-08-30: 50%
2 | N22 | 480 SQ YD | Real Infra | 2025-07-29 | 2025-08-24 | 2025-11-17 | 2026-08-23 | 2027-02-28 | 15.6 | 95% | 40% | 6.0667 | COMPLETE |  | 2026-10-12 |  | 2026-11-25 |  | 2026-12-09 | 2026-12-30 | 2027-01-29 |  | 2027-02-13 | 2027-02-23 | 40% | 40% | 40% | 2026-08-10: 40%; 2026-08-20: 40%; 2026-08-30: 40%
3 | N26 | 545 SQ YD | Real Infra | 2025-06-28 | 2025-08-15 | 2025-11-18 | 2026-08-14 | 2027-02-28 | 15.5667 | 95% | 35% | 6.0667 | COMPLETE |  | 2026-10-12 |  | 2026-11-25 |  | 2026-12-09 | 2026-12-30 | 2027-01-29 |  | 2027-02-13 | 2027-02-23 | 30% | 30% | 30% | 2026-08-10: 30%; 2026-08-20: 30%; 2026-08-30: 35%
4 | N36 | 317 SQ YD | Real Infra | 2025-05-23 | 2025-06-24 | 2025-11-11 | 2026-06-23 | 2027-02-28 | 15.8 | 100% | 38% | 6.0667 | COMPLETE |  | 2026-08-31 |  | 2026-10-20 |  | 2026-12-09 | 2026-12-30 | 2027-01-29 |  | 2027-02-13 | 2027-02-23 | 38% | 38% | 38% | 2026-08-10: 38%; 2026-08-20: 38%; 2026-08-30: 38%
5 | S50 | 317 SQ TD | AVS | 2025-09-20 | 2025-06-06 | 2025-05-15 | 2026-08-05 | 2027-03-31 | 22.8333 | 100% | 60% | 7.1 | COMPLETE |  | 2026-08-15 |  | 2026-10-15 |  | 2027-01-09 | 2027-01-30 | 2027-03-01 |  | 2027-03-16 | 2027-03-26 | 45% | 50% | 50% | 2026-08-10: 50%; 2026-08-20: 55%; 2026-08-30: 60%
6 | N29 | 216 SQ YD | Z Square | 2025-07-31 | 2025-09-06 | 2025-12-16 | 2026-09-05 | 2027-04-30 | 16.6667 | 90% | 30% | 8.1 | 2026-07-10 | 2026-08-01 | 2026-09-10 |  | 2026-11-08 |  | 2027-02-08 | 2027-03-01 | 2027-03-31 |  | 2027-04-15 | 2027-04-25 | 20% | 20% | 20% | 2026-08-10: 25%; 2026-08-20: 30%; 2026-08-30: 30%
7 | S40 | 163 SQ YD | BRICKS | 2026-03-16 | 2026-04-24 | 2026-05-13 | 2027-04-23 | 2027-05-31 | 12.7667 |  | 20% | 9.1333 | 2026-08-19 |  | 2026-10-13 |  | 2027-02-21 |  | 2027-03-11 | 2027-04-01 | 2027-05-01 |  | 2027-05-16 | 2027-05-26 | 10% | 10% | 10% | 2026-08-10: 10%; 2026-08-20: 15%; 2026-08-30: 20%
8 | N66 | 216 SQ YD | Z Square | 2025-10-27 | 2026-02-24 | 2026-02-20 | 2027-02-23 | 2027-06-30 | 16.5 | 40% | 20% | 10.1333 | 2026-07-15 |  | 2026-09-06 |  | 2026-12-05 |  | 2027-04-10 | 2027-05-01 | 2027-05-31 |  | 2027-06-15 | 2027-06-25 | 15% | 20% | 20% | 2026-08-10: 20%; 2026-08-20: 20%; 2026-08-30: 20%
9 | N12A | 216 SQ YD | Z Square | 2026-01-01 | 2026-02-20 | 2026-02-20 | 2027-02-19 | 2027-06-30 | 16.5 | 40% | 15% | 10.1333 | 2026-07-30 |  | 2026-09-28 |  | 2026-12-31 |  | 2027-04-10 | 2027-05-01 | 2027-05-31 |  | 2027-06-15 | 2027-06-25 | 15% | 15% | 15% | 2026-08-10: 15%; 2026-08-20: 15%; 2026-08-30: 15%
10 | S38 | 216 SQ YD | BRICKS | 2026-03-16 | 2026-04-24 | 2026-05-13 | 2027-04-23 | 2027-06-30 | 13.7667 |  | 20% | 10.1333 | 2026-08-06 |  | 2026-11-13 |  | 2027-02-08 |  | 2027-04-10 | 2027-05-01 | 2027-05-31 |  | 2027-06-15 | 2027-06-25 | 15% | 15% | 15% | 2026-08-10: 15%; 2026-08-20: 20%; 2026-08-30: 20%
11 | S54 | 421 SQ YD | AVS | 2025-05-28 | 2026-01-21 | 2026-01-21 | 2027-01-20 | 2027-06-30 | 17.5 | 50% | 30% | 10.1333 | COMPLETE |  | 2026-10-25 |  | 2026-12-31 |  | 2027-04-10 | 2027-05-01 | 2027-05-31 |  | 2027-06-15 | 2027-06-25 | 25% | 25% | 25% | 2026-08-10: 25%; 2026-08-20: 30%; 2026-08-30: 30%
12 | S60 | 545 SQ YD | AVS | 2025-01-21 | 2025-02-24 | 2025-05-13 | 2026-02-23 | 2027-06-30 | 25.9333 | 100% | 40% | 10.1333 | COMPLETE |  | 2026-10-25 |  | 2026-12-31 |  | 2027-04-10 | 2027-05-01 | 2027-05-31 |  | 2027-06-15 | 2027-06-25 | 27% | 30% | 30% | 2026-08-10: 35%; 2026-08-20: 40%; 2026-08-30: 40%
13 | S34 | 492 SQ YD | BRICKS | 2026-03-11 | 2026-04-15 | 2026-05-02 | 2027-07-14 | 2027-07-31 | 15.1667 |  | 20% | 11.1667 | 2026-08-30 |  | 2026-11-15 |  | 2027-02-28 |  | 2027-05-11 | 2027-06-01 | 2027-07-01 |  | 2027-07-16 | 2027-07-26 | 10% | 10% | 10% | 2026-08-10: 10%; 2026-08-20: 15%; 2026-08-30: 20%
14 | S10 | 216 SQ YD | Dira | 2026-02-25 | 2026-04-06 | 2026-05-17 | 2027-04-05 | 2027-07-31 | 14.6667 |  | 5% | 11.1667 | 2026-09-25 |  | 2026-12-31 |  | 2027-03-31 |  | 2027-05-11 | 2027-06-01 | 2027-07-01 |  | 2027-07-16 | 2027-07-26 | 5% | 5% | 5% | bar: 2026-08-10 to 2026-08-30
15 | N15 | 216 SQ YD | Nirvay Infra | 2026-02-21 | 2026-04-06 | 2026-05-21 | 2027-04-05 | 2027-07-31 | 14.5333 |  | 15% | 11.1667 | 2026-08-30 |  | 2026-12-15 |  | 2027-03-20 |  | 2027-05-11 | 2027-06-01 | 2027-07-01 |  | 2027-07-16 | 2027-07-26 | 5% | 5% | 5% | 2026-08-10: 10%; 2026-08-20: 10%; 2026-08-30: 15%
16 | S02 | 494 SQ YD | BRICKS | 2026-01-29 | 2026-02-15 | 2026-02-20 | 2027-02-14 | 2027-07-31 | 17.5333 |  | 20% | 11.1667 | 2026-07-22 |  | 2026-10-05 |  | 2027-01-03 |  | 2027-05-11 | 2027-06-01 | 2027-07-01 |  | 2027-07-16 | 2027-07-26 | 18% | 20% | 20% | 2026-08-10: 20%; 2026-08-20: 20%; 2026-08-30: 20%
17 | S04 | 216 SQ YD | BRICKS | 2026-05-22 | 2026-06-15 | 2026-06-04 | 2027-04-30 | 2027-08-14 | 14.5333 |  | 5% | 11.6333 | 2026-08-31 |  | 2027-12-15 |  | 2027-03-13 |  | 2027-05-25 | 2027-06-15 | 2027-07-15 |  | 2027-07-30 | 2027-08-09 | 5% | 5% | 5% | bar: 2026-08-10 to 2026-08-30
18 | N16 | 587 SQ YD | Nirvay Infra | 2026-03-31 | 2026-05-06 | 2026-05-21 | 2027-08-05 | 2027-10-31 | 17.6 |  | 15% | 14.2333 | 2026-09-30 |  | 2026-12-31 |  | 2027-05-31 |  | 2027-08-11 | 2027-09-01 | 2027-10-01 |  | 2027-10-16 | 2027-10-26 | 5% | 5% | 5% | 2026-08-10: 10%; 2026-08-20: 10%; 2026-08-30: 15%
19 | S12A | 317 SQ YD | Dira | 2026-02-10 | 2026-05-06 | 2026-05-17 | 2027-08-05 | 2027-10-31 | 17.7333 |  | 5% | 14.2333 | 2026-09-15 |  | 2026-12-15 |  | 2027-05-15 |  | 2027-08-11 | 2027-09-01 | 2027-10-01 |  | 2027-10-16 | 2027-10-26 | 5% | 5% | 5% | bar: 2026-08-10 to 2026-08-30
20 | S06 | 317 SQ YD | BRICKS | 2026-06-01 | 2026-06-15 | 2026-06-04 | 2027-06-30 | 2027-11-15 | 17.6333 |  | 10% | 14.7333 | 2026-09-20 |  | 2026-12-31 |  | 2027-05-30 |  | 2027-08-26 | 2027-09-16 | 2027-10-16 |  | 2027-10-31 | 2027-11-10 | 5% | 5% | 5% | 2026-08-10: 5%; 2026-08-20: 5%; 2026-08-30: 10%
21 | S 07/08 | 494 SQ YD |  |  | 2026-09-30 |  | 2028-03-30
22 | N64 | 351 SQ YD |  |  | 2026-09-30 |  | 2028-03-30
23 | N53 | 317 SQ YD |  |  | 2026-09-30 |  | 2028-03-30
24 | N 6/78 | 285 SQ YD |  |  | 2026-09-15 |  | 2027-12-14
25 | N11 | 317 SQ YD |  |  | 2026-09-15 |  | 2028-03-14
26 | S32 | 285 SQ YD |  |  | 2026-09-15 |  | 2027-12-14
|  | GF Unit |  |  |  | GF + FF Unit
| Stage 1 | PLINTH |  |  |  | PLINTH
| Stage 2 | RCC |  |  |  | RCC
| Stage 3 | MASONARY PLASTER+ MEP (concealed) |  |  |  | MASONARY PLASTER+ MEP (concealed)
| Stage 4 | FINISHING |  |  |  | FINISHING
Formulas:
Doors, Windows & Cobble Order placed = [Doors, Windows & Cobble received]-21
Doors, Windows & Cobble received = [Stage 4]-30

## 24th July status (hidden)
The Sage By Repose
| Villa Progress Report -22 JUN 2026 |  |  |  | Start Date |  | Possession Date |  | Actual timel to delivery (months) | Over all Work % as on date |  | Stage 1 |  | Stage2 |  | Stage 3 |  | Stage 4
Sr. No | Villa No. | Villa type (BHK) | Contractor Name | Customer Signature Date | Committed | Actual | Committed | Actual |  | Committed | Actual | Committed | Actual | Committed | Actual | Committed | Actual | Committed | Actual | QC + CRM inspection | CRM handover
1 | N3A | 421 SQ YD | Real Infra | 2025-03-19 | 2025-04-06 | 2025-05-20 | 2026-04-05 | 2026-11-30 | 18.6333 | 100% | 60% | [6 empty] | 2026-10-17 |  | 2026-11-01 | 2026-11-11
2 | N05 | 216 SQ YD | Real Infra | 2025-01-22 | 2025-02-24 | 2025-04-15 | 2026-02-23 | 2026-08-31 | 16.7667 | 100% | 92% | [6 empty] | 2026-06-30 |  | 2026-07-15 | 2026-07-25
3 | N09 | 480 SQ YD | Real Infra | 2025-07-09 | 2025-08-24 | 2025-11-18 | 2026-08-23 | 2026-12-31 | 13.6 | 95% | 40% | [6 empty] | 2026-11-30 |  | 2026-12-15 | 2026-12-25
4 | N10 | 216 SQ YD | Real Infra | 2025-01-20 | 2025-02-15 | 2025-04-18 | 2026-02-14 | 2026-07-31 | 15.6333 | 100% | 95% | [6 empty] | 2026-07-01 |  | 2026-07-16 | 2026-07-26
5 | N12A | 216 SQ YD | Z Square | 2026-01-01 | 2026-02-20 | 2026-02-20 | 2027-02-19 | 2027-06-30 | 16.5 | 40% | 15% | [6 empty] | 2027-05-31 |  | 2027-06-15 | 2027-06-25
6 | N14 | 216 SQ YD | Real infra | 2025-06-21 | 2025-07-24 | 2025-11-12 | 2026-07-23 | 2026-11-30 | 12.7667 | 100% | 45% | [6 empty] | 2026-10-31 |  | 2026-11-15 | 2026-11-25
7 | N15 | 216 SQ YD | Nirvay Infra | 2026-02-21 | 2026-04-06 | 2026-05-21 | 2027-04-05 | 2027-07-31 | 14.5333 |  | 5% | [6 empty] | 2027-07-01 |  | 2027-07-16 | 2027-07-26
8 | N16 | 587 SQ YD | Nirvay Infra | 2026-03-31 | 2026-05-06 | 2026-05-21 | 2027-08-05 | 2027-11-30 | 18.6 |  | 5% | [6 empty] | 2027-10-31 |  | 2027-11-15 | 2027-11-25
9 | N22 | 480 SQ YD | Real Infra | 2025-07-29 | 2025-08-24 | 2025-11-17 | 2026-08-23 | 2027-02-28 | 15.6 | 95% | 38% | [6 empty] | 2027-01-29 |  | 2027-02-13 | 2027-02-23
10 | N26 | 545 SQ YD | Real Infra | 2025-06-28 | 2025-08-15 | 2025-11-18 | 2026-08-14 | 2027-02-28 | 15.5667 | 95% | 30% | [6 empty] | 2027-01-29 |  | 2027-02-13 | 2027-02-23
11 | N27 | 216 SQ YD | Real Infra | 2025-04-22 | 2025-05-24 | 2025-05-20 | 2026-05-23 | 2026-10-30 | 17.6 | 100% | 60% | [6 empty] | 2026-09-30 |  | 2026-10-15 | 2026-10-25
12 | N29 | 216 SQ YD | Z Square | 2025-07-31 | 2025-09-06 | 2025-12-16 | 2026-09-05 | 2027-04-30 | 16.6667 | 90% | 18% | [6 empty] | 2027-03-31 |  | 2027-04-15 | 2027-04-25
13 | N36 | 317 SQ YD | Real Infra | 2025-05-23 | 2025-06-24 | 2025-11-11 | 2026-06-23 | 2027-02-28 | 15.8 | 100% | 38% | [6 empty] | 2027-01-29 |  | 2027-02-13 | 2027-02-23
14 | N62 | 216 SQ YD | Real Infra | 2025-02-06 | 2025-03-15 | 2025-04-17 | 2026-03-14 | 2026-08-11 | 16.0333 | 100% | 80% | [6 empty] | 2026-07-12 |  | 2026-07-27 | 2026-08-06
15 | N66 | 216 SQ YD | Z Square | 2025-10-27 | 2026-02-24 | 2026-02-20 | 2027-02-23 | 2027-06-30 | 16.5 | 40% | 15% | [6 empty] | 2027-05-31 |  | 2027-06-15 | 2027-06-25
16 | S02 | 494 SQ YD | BRICKS | 2026-01-29 | 2026-02-15 | 2026-02-20 | 2027-02-14 | 2027-08-31 | 18.5667 |  | 18% | [6 empty] | 2027-08-01 |  | 2027-08-16 | 2027-08-26
17 | S04 | 239 SQ YD | BRICKS | 2026-05-22 | 2026-06-15 | 2026-06-04 | 2027-04-30 | 2027-09-14 | 15.5667 |  | 2% | [6 empty] | 2027-08-15 |  | 2027-08-30 | 2027-09-09
18 | S06 | 317 SQ YD | BRICKS | 2026-06-01 | 2026-06-15 | 2026-06-04 | 2027-06-30 | 2027-12-15 | 18.6333 |  | 5% | [6 empty] | 2027-11-15 |  | 2027-11-30 | 2027-12-10
19 | S10 | 216 SQ YD | VAIDEHI | 2026-02-25 | 2026-04-06 | 2026-05-17 | 2027-04-05 | 2027-07-31 | 14.6667 |  | 5% | [6 empty] | 2027-07-01 |  | 2027-07-16 | 2027-07-26
20 | S12A | 317 SQ YD | VAIDEHI | 2026-02-10 | 2026-05-06 | 2026-05-17 | 2027-08-05 | 2027-11-30 | 18.7333 |  | 5% | [6 empty] | 2027-10-31 |  | 2027-11-15 | 2027-11-25
21 | S14 | 351 SQ YD | AVS | 2025-04-30 | 2025-06-06 | 2025-06-06 | 2026-06-05 | 2026-10-15 | 16.5333 | 100% | 85% | [6 empty] | 2026-09-15 |  | 2026-09-30 | 2026-10-10
22 | S18 | 163 SQ YD | AVS | 2025-01-24 | 2025-02-24 | 2025-05-15 | 2026-02-23 | 2026-09-30 | 16.7667 | 100% | 90% | [6 empty] | 2026-08-31 |  | 2026-09-15 | 2026-09-25
23 | S30 | 351 SQ YD | AVS | 2025-05-22 | 2025-06-15 | 2025-06-09 | 2026-06-14 | 2026-12-31 | 19 | 100% | 75% | [6 empty] | 2026-12-01 |  | 2026-12-16 | 2026-12-26
24 | S34 | 492 SQ YD | BRICKS | 2026-03-11 | 2026-04-15 | 2026-05-02 | 2027-07-14 | 2027-07-31 | 15.1667 |  | 5% | [6 empty] | 2027-07-01 |  | 2027-07-16 | 2027-07-26
25 | S37 | 285 SQ YD | AVS | 2025-06-11 | 2025-06-24 | 2025-11-23 | 2026-06-23 | 2027-02-15 | 14.9667 | 100% | 48% | [6 empty] | 2027-01-16 |  | 2027-01-31 | 2027-02-10
26 | S38 | 239 SQ YD | BRICKS | 2026-03-16 | 2026-04-24 | 2026-05-13 | 2027-04-23 | 2027-06-30 | 13.7667 |  | 10% | [6 empty] | 2027-05-31 |  | 2027-06-15 | 2027-06-25
27 | S40 | 163 SQ YD | BRICKS | 2026-03-16 | 2026-04-24 | 2026-05-13 | 2027-04-23 | 2027-05-31 | 12.7667 |  | 5% | [6 empty] | 2027-05-01 |  | 2027-05-16 | 2027-05-26
28 | S50 | 317 SQ TD | AVS | 2025-09-20 | 2025-06-06 | 2025-05-15 | 2026-08-05 | 2027-03-31 | 22.8333 | 100% | 45% | [6 empty] | 2027-03-01 |  | 2027-03-16 | 2027-03-26
29 | S54 | 421 SQ YD | AVS | 2025-05-28 | 2026-01-21 | 2026-01-21 | 2027-01-20 | 2027-06-30 | 17.5 | 50% | 25% | [6 empty] | 2027-05-31 |  | 2027-06-15 | 2027-06-25
30 | S60 | 545 SQ YD | AVS | 2025-01-21 | 2025-02-24 | 2025-05-13 | 2026-02-23 | 2027-06-30 | 25.9333 | 100% | 27% | [6 empty] | 2027-05-31 |  | 2027-06-15 | 2027-06-25
|  | GF Unit |  |  |  | GF + FF Unit
| Stage 1 | GF slab |  |  |  | GF slab
| Stage 2 | GF columns + Beam + Terrace Slab |  |  |  | GF columns + Beam + FF Slab
| Stage 3 | Masonary Complete + MEP |  |  |  | Terrace slab + Masonary Complete + MEP
| Stage 4 | Completion upto Windows+façade+Ladnscape |  |  |  | Completion upto Windows+façade+Ladnscape
Formulas:
Stage 4 = [QC + CRM inspection]-15
CRM handover = [QC + CRM inspection]+10
QC + CRM inspection = [Actual]-15

## Villa timeline (site report) (hidden)
Villa Progress Report -22 JUN 2026
Site : Suryam The Sage By Repose - Lohr
Sr. No | Villa No. | Villa type (BHK) | Contractor Name | Customer Signature Date | Start date | Possession Date | Actual Start Date | Actual Possession date | Over all Work % | WORK | EXTRA WORK | Completion Status as per CRM TEAM suggestion
Group B-2017-2018
1 | A-87-88 | 2 -B | K.D.Const. Mevada |  | 19.05.2017 |  |  |  | 100% |  | Done
2 | B-56 | 2-A | SSC |  | 04.06.2017 |  |  |  | 100% |  | Done
3 | B-57 | 2-A | HCC |  | 02.01.2018 |  |  |  | 100% |  | Done
4 | B-66 | 2-A | HCC |  | 02.01.2018 |  |  |  | 100% |  | Done
5 | B-72 | 2-B | SSC |  | 01.08.2017 |  |  |  | 100% |  | Done
6 | B-73 | 2-C | HCC |  | 08.10.2017 |  |  |  | 100% |  | Done
7 | B-74/75 | 2-C | HCC |  | 01.08.2017 |  |  |  | 100% |  | Done
8 | B-76 | 1 WI | HCC |  | 01.08.2017 |  |  |  | 100% |  | Done
9 | B-88/89 | 2- A /0 | HCC |  | 20.05.2017 |  |  |  | 100% |  | Done
10 | B-134/135/ 136 | 2 -C | SSC |  | 05.05.2017 |  |  |  | 100% |  | Done
11 | B-158/159 | 2-A | SSC |  | 15.08.2017 |  |  |  | 100% |  | Done
12 | B-170 to173 | 2-spe. | K.D.Const. Mevada |  | 10.11.2017 |  |  |  | 100% |  | Done
13 | B-178 | 1-WI | K.D.Const. Mevada |  | 20.05.2017 |  |  |  | 100% |  | Done
14 | B-169 | 2-A | K.D.Const. Mevada |  | 20.05.2017 |  |  |  | 100% |  | Done
15 | B-179 | 1-WI | K.D.Const. Mevada |  | 10.11.2017 |  |  |  | 100% |  | Done
16 | B-182-183-199-200 | 2-A/ 0 | K.D.Const. Mevada |  | 20.05.2017 |  |  |  | 100% |  | Done
17 | B-194/195 | 2-A | K.D.Const. Mevada |  | 19.08.2017 |  |  |  | 100% |  | Done
18 | C-127 | 1 WI | SSC |  | 10.01.2018 |  |  |  | 100% |  | Done
Group C-2018-2019
1 | B-22/23 | 2-C | K.C. |  | 10.05.2018 |  |  |  | 100% |  | Done
2 | B-147 | 1- | K.C. |  | 10.05.2018 |  |  |  | 100% |  | Done
3 | C-27-28 | 2-C | K.C. |  | 10.07.2018 |  |  |  | 100% |  | Done
4 | C-158 | 1- | K.C. |  | 16.05.2018 |  |  |  | 100% |  | Done
5 | C-173 | 1- | K.C. |  | 16.05.2018 |  |  |  | 100% |  | Done
6 | D-32-33 | 2 | K.C. |  | 01.07.2018 |  |  |  | 100% |  | Done
7 | D-76 | 1-160 | K.C. |  | 01.07.2018 |  |  |  | 100% |  | Done
Group D-2019-2020
1 | A-06 | 2-A | K.D. |  | 01.07.2019 |  |  |  | 100% |  | Done
2 | A-24 | 2-A | HCC |  | 15.04.19 |  |  |  | 100% |  | Done
3 | B-20/21 | 2-B | HCC |  | 05.01.2019 |  |  |  | 100% |  | Done
4 | A-93-94 | 2-/0 | K.D.Const. Mevada |  | 01.07.2019 |  |  |  | 100% |  | Done
5 | B-33 | 2-A | HCC |  | 20.12.2020 |  |  |  | 100% |  | Done
6 | B-37-38 | 2-B | HCC |  | 15.11.2019 |  |  |  | 100% |  | Done
7 | B-77 | 2-B | HCC |  | 05.01.2019 |  |  |  | 100% |  | Done
8 | B-107 | 2-B | HCC |  | 01.02.2019 |  |  |  | 100% |  | Done
9 | B-108 | 2-C | HCC |  | 15.05.2019 |  |  |  | 100% |  | Done
10 | B-141 | 2 | K.D. |  | 25.12.2019 |  |  |  | 100% |  | Done
11 | B-146 | 1 | K.D. |  | 07.12.2019 |  |  |  | 100% |  | Done
12 | B-144 | 1-160 | K.D. |  | 16.01.2020 |  |  |  | 100% |  | Done
13 | B-149 | 2 | K.D. |  | 05.01.2020 |  |  |  | 100% |  | Done
14 | B-164 | 2-C | HCC |  | 05.01.2019 |  |  |  | 100% |  | Done
15 | B-203 | 2-B | HCC |  | 05.05.2019 |  |  |  | 100% |  | Done
16 | C-09 | 2-A | HCC |  | 16.01.2020 |  |  |  | 100% |  | Done
17 | C-21 | 2-B | K.D. |  | 27.01.2020 |  |  |  | 100% |  | Done
18 | C-64 | 1-WI | K.D. |  | 16.01.2020 |  |  |  | 100% |  | Done
19 | C-78-79 | 2-New | HCC |  | 20.12.2019 |  |  |  | 100% |  | Done
20 | C-143 | 1-W | HCC |  | 18.01.2019 |  |  |  | 100% |  | Done
21 | C-161 | 1-WI | HCC |  | 18.01.2019 |  |  |  | 100% |  | Done
22 | C-174 | 1-WI | HCC |  | 20.12.2019 |  |  |  | 100% |  | Done
23 | C-207 | 1-WI | HCC |  | 15.04.2019 |  |  |  | 100% |  | Done
24 | D-13 | 2-B | HCC |  | 15.05.2019 |  |  |  | 100% |  | Done
25 | D-17-18 | 2-B | HCC |  | 16.01.2020 |  |  |  | 100% |  | Done
26 | D-69/70/77/78 | 2-B | K.D. |  | 30.05.2019 |  |  |  | 100% |  | Done
27 | D-86 | 1-W | HCC |  | 12.03.2019 |  |  |  | 100% |  | Done
28 | D-88 | 1-W | K.D. |  | 01.08.2019 |  |  |  | 100% |  | Done
29 | D-89 | 2-B | HCC |  | 25.02.2019 |  |  |  | 100% |  | Done
30 | C-205/206 | 2-B | K.D. |  | 23.06.2019 |  |  |  | 100% |  | Done
31 | A-93/94 | 2-B/0 | K.D. |  | 01.07.2019 |  |  |  | 100% |  | Done
32 | C-82-83-102-103 | 2-B | K.D. |  | 01.07.2020 |  |  |  | 100% |  | Done
33 | D-94 | 2-B | HCC |  | 01.07.2020 |  |  |  | 100% |  | Done
34 | D-07-08 | 2-B | K.D. |  | 15.08.2020 |  |  |  | 100% |  | Done
35 | D-81 | 2-A | HCC |  | 25.03.2020 |  |  |  | 100% |  | Done
36 | B-47 | 2-A/ Studio | HCC |  | 20.07.2020 | 05.09.2021 |  |  | 100% |  | Done
Group E- 2020-2021
North Villa
1 | N3A | 421 SQ YD | Real Infra | 2025-03-19 | 2025-04-06 | 2026-04-05 | 2025-05-20 | 2026-11-30 | 60% | FIRST FLOOR BRICK WORK . GROUND FLOOR INTERNAL PLASTER WORK |  | 50%
2 | N05 | 216 SQ YD | Real Infra | 2025-01-22 | 2025-02-24 | 2026-02-23 | 2025-04-15 | 2026-08-31 | 92% | INTERNALS PLUMBING WORK . VILLA OUTER DEVLOPMENT WORK . TILES WORK IN PROGRESS. |  | 75%
3 | N09 | 480 SQ YD | Real Infra | 2025-07-09 | 2025-08-24 | 2026-08-23 | 2025-11-18 | 2026-12-31 | 40% | GROUND FLOOR SLAB STEEL WORK |  | 50%
4 | N10 | 216 SQ YD | Real Infra | 2025-01-20 | 2025-02-15 | 2026-02-14 | 2025-04-18 | 2026-07-31 | 95% | VILLA OUTER DEVLOPMENT & INTERNALS TILES WORK |  | 75%
5 | N12A | 216 SQ YD | Z Square | 2026-01-01 | 2026-02-20 | 2027-02-19 | 2026-02-20 | 2027-06-30 | 15% | GROUND BEAM STEEL WORK |  | 25%
6 | N14 | 216 SQ YD | Real infra | 2025-06-21 | 2025-07-24 | 2026-07-23 | 2025-11-12 | 2026-09-30 | 45% | SLAB STEEL WORK |  | 50%
7 | N15 | 216 SQ YD | Nirvay Infra | 2026-02-21 | 2026-04-06 | 2027-04-05 | 2026-05-21 | 2027-07-31 | 5% | PILE WORK | 1.4 M KITCHEN PLATFORMS ADDED / SINK & STOVE LOCTION REVISED / OVERHEAD TANK PLACED ABOVE ONE OF THE BADROOM. | 25%
8 | N16 | 587 SQ YD | Nirvay Infra | 2026-03-31 | 2026-05-06 | 2027-08-05 | 2026-05-21 | 2027-11-30 | 5% | PILE WORK |  | 25%
9 | N22 | 480 SQ YD | Real Infra | 2025-07-29 | 2025-08-24 | 2026-08-23 | 2025-11-17 | 2026-12-31 | 38% | GROUND FLOOR BRICK WORK LINTAL LVL |  | 50%
10 | N26 | 545 SQ YD | Real Infra | 2025-06-28 | 2025-08-15 | 2026-08-14 | 2025-11-18 | 2026-12-31 | 30% | GROUND FLOOR BRICK WORK LINTAL LVL |  | 50%
11 | N27 | 216 SQ YD | Real Infra | 2025-04-22 | 2025-05-24 | 2026-05-23 | 2025-05-20 | 2026-10-30 | 60% | OUTER PLASTER WORK |  | 75%
12 | N29 | 216 SQ YD | Z Square | 2025-07-31 | 2025-09-06 | 2026-09-05 | 2025-12-16 | 2027-04-30 | 18% | GB BEAM & PILE CAP DE SHUTTERING WORK |  | 25%
13 | N36 | 317 SQ YD | Real Infra | 2025-05-23 | 2025-06-24 | 2026-06-23 | 2025-11-11 | 2026-12-31 | 38% | GF FLOOR SLAB STEEL WORK |  | 50%
14 | N62 | 216 SQ YD | Real Infra | 2025-02-06 | 2025-03-15 | 2026-03-14 | 2025-04-17 | 2026-08-11 | 80% | VILLA OUTER DEVLOPMENT WORK & TILES WORK | TOILET DOOR DIRECTION CHANGE & URINAL REMOVED FROM DAY TOILET | 75%
15 | N66 | 216 SQ YD | Z Square | 2025-10-27 | 2026-02-24 | 2027-02-23 | 2026-02-20 | 2027-06-30 | 15% | GB BEAM & PILE CAP STEEL WORK |  | 25%
South Villa
16 | S02 | 494 SQ YD | BRICKS INFRA | 2026-01-29 | 2026-02-15 | 2027-02-14 | 2026-02-20 | 2027-05-31 | 18% | GF COLUMN CASTING WORK |  | 25%
17 | S04 | 239 SQ YD | BRICKS INFRA | 2026-05-22 | 2026-06-15 | 2027-09-14 | 2026-06-04 | 2027-04-30 | 2% | PILE CAGE WORK | STORE DOOR HAS SHIFTED IN THE CENTER OF THE STORE. | 25%
18 | S06 | 317 SQ YD | BRICKS INFRA | 2026-06-01 | 2026-06-15 | 2027-12-14 | 2026-06-04 | 2027-06-30 | 5% | PILE WORK DONE EXCAWATION START |  | 25%
19 | S10 | 216 SQ YD | VAIDEHI | 2026-02-25 | 2026-04-06 | 2027-04-05 | 2026-05-17 | 2027-07-31 | 5% | PILE CAGE WORK |  | 25%
20 | S12A | 317 SQ YD | VAIDEHI | 2026-02-10 | 2026-05-06 | 2027-08-05 | 2026-05-17 | 2027-11-30 | 5% | PILE WORK DONE |  | 25%
21 | S14 | 351 SQ YD | AVS | 2025-04-30 | 2025-06-06 | 2026-06-05 | 2025-06-06 | 2026-10-15 | 85% | TILES & PLUMBING WORK & OUTER DEVLOPMENT WORK |  | 75%
22 | S18 | 163 SQ YD | AVS | 2025-01-24 | 2025-02-24 | 2026-02-23 | 2025-05-15 | 2026-09-30 | 90% | OUTER DEVLOPMENT WORK & INTERNAL TILES WORK |  | 75%
23 | S30 | 351 SQ YD | AVS | 2025-05-22 | 2025-06-15 | 2026-06-14 | 2025-06-09 | 2026-10-31 | 75% | OUTER PLASTER WORK | NEAR KITCHEN THREE WALL CHANGES/ NT ADDED | 75%
24 | S34 | 492 SQ YD | BRICKS INFRA | 2026-03-11 | 2026-04-15 | 2027-07-14 | 2026-05-02 | 2027-07-31 | 5% | PILE CAP EXCAVTION WORK |  | 25%
25 | S37 | 285 SQ YD | AVS | 2025-06-11 | 2025-06-24 | 2026-06-23 | 2025-11-23 | 2026-12-15 | 48% | SLAB STEELWORK |  | 50%
26 | S38 | 239 SQ YD | BRICKS INFRA | 2026-03-16 | 2026-04-24 | 2027-04-23 | 2026-05-13 | 2027-05-31 | 10% | PILE CAP PCC WORK |  | 25%
27 | S40 | 163 SQ YD | BRICKS INFRA | 2026-03-16 | 2026-04-24 | 2027-04-23 | 2026-05-13 | 2027-06-30 | 5% | PILE CAP EXCAVTION WORK |  | 25%
28 | S50 | 317 SQ TD | AVS | 2025-09-20 | 2025-06-06 | 2026-08-05 | 2025-05-15 | 2026-12-15 | 45% | GF SLAB SHUTTERING WORK | 5 CHANGES ADD CORTYUARD, DAY TOILET DOOR ,URINAL REMOVE, WC SHIFTED, L SHAPE KITCHAN | 50%
29 | S54 | 421 SQ YD | AVS | 2025-05-28 | 2026-01-21 | 2027-01-20 | 2026-01-21 | 2027-03-15 | 25% | COLUMN STARTER WORK |  | 50%
30 | S60 | 545 SQ YD | AVS | 2025-01-21 | 2025-02-24 | 2026-02-23 | 2025-05-13 | 2027-02-28 | 27% | COLUMN STARTER WORK |  | 50%
|  | Project Manager |  |  | AGM Projects |  | Director Operations
Sign/Date
|  | Hasmukhbhai Patel |  |  | Adarshbhai Gupta |  | Hiteshbhai Patel

## Villa timeline Jj (hidden)
The Sage By Repose
| Villa Progress Report -22 JUN 2026 |  |  |  | Strt Date |  | Possession Date
Sr. No | Villa No. | Villa type (BHK) | Contractor Name | Customer Signature Date | Sign off | Actual | Sign off | Actual | Diff in new possession date (months) | Over all Work % | 2026-06-26 | Delay Days | Delay in Months | Actual time Taken Days | Actual time Taken Months
1 | N3A | 421 SQ YD | Real Infra | 2025-03-19 | 2025-04-06 | 2025-05-20 | 2026-04-05 | 2026-11-30 |  | 60% | 157 | 239 | 7.9667 | 603 | 20.1
2 | N05 | 216 SQ YD | Real Infra | 2025-01-22 | 2025-02-24 | 2025-04-15 | 2026-02-23 | 2026-08-31 |  | 92% | 66 | 189 | 6.3 | 553 | 18.4333
3 | N09 | 480 SQ YD | Real Infra | 2025-07-09 | 2025-08-24 | 2025-11-18 | 2026-08-23 | 2026-12-31 |  | 40% | 188 | 130 | 4.3333 | 494 | 16.4667
4 | N10 | 216 SQ YD | Real Infra | 2025-01-20 | 2025-02-15 | 2025-04-18 | 2026-02-14 | 2026-07-31 |  | 95% | 35 | 167 | 5.5667 | 531 | 17.7
5 | N12A | 216 SQ YD | Z Square | 2026-01-01 | 2026-02-20 | 2026-02-20 | 2027-02-19 | 2027-06-30 | 4.3667 | 15% |  | 131 | 4.3667 | 495 | 16.5
6 | N14 | 216 SQ YD | Real infra | 2025-06-21 | 2025-07-24 | 2025-11-12 | 2026-07-23 | 2026-11-30 |  | 45% | 157 | 130 | 4.3333 | 494 | 16.4667
7 | N15 | 216 SQ YD | Nirvay Infra | 2026-02-21 | 2026-04-06 | 2026-05-21 | 2027-04-05 | 2027-07-31 | 3.9 | 5% |  | 117 | 3.9 | 481 | 16.0333
8 | N16 | 587 SQ YD | Nirvay Infra | 2026-03-31 | 2026-05-06 | 2026-05-21 | 2027-08-05 | 2027-11-30 | 3.9 | 5% |  | 117 | 3.9 | 573 | 19.1
9 | N22 | 480 SQ YD | Real Infra | 2025-07-29 | 2025-08-24 | 2025-11-17 | 2026-08-23 | 2027-02-28 | 6.3 | 38% | 247 | 189 | 6.3 | 553 | 18.4333
10 | N26 | 545 SQ YD | Real Infra | 2025-06-28 | 2025-08-15 | 2025-11-18 | 2026-08-14 | 2027-02-28 | 6.6 | 30% | 247 | 198 | 6.6 | 562 | 18.7333
11 | N27 | 216 SQ YD | Real Infra | 2025-04-22 | 2025-05-24 | 2025-05-20 | 2026-05-23 | 2026-10-30 |  | 60% | 126 | 160 | 5.3333 | 524 | 17.4667
12 | N29 | 216 SQ YD | Z Square | 2025-07-31 | 2025-09-06 | 2025-12-16 | 2026-09-05 | 2027-04-30 | 7.9 | 18% | 308 | 237 | 7.9 | 601 | 20.0333
13 | N36 | 317 SQ YD | Real Infra | 2025-05-23 | 2025-06-24 | 2025-11-11 | 2026-06-23 | 2027-02-28 | 8.3333 | 38% | 247 | 250 | 8.3333 | 614 | 20.4667
14 | N62 | 216 SQ YD | Real Infra | 2025-02-06 | 2025-03-15 | 2025-04-17 | 2026-03-14 | 2026-08-11 |  | 80% | 46 | 150 | 5 | 514 | 17.1333
15 | N66 | 216 SQ YD | Z Square | 2025-10-27 | 2026-02-24 | 2026-02-20 | 2027-02-23 | 2027-06-30 | 4.2333 | 15% |  | 127 | 4.2333 | 491 | 16.3667
16 | S02 | 494 SQ YD | BRICKS | 2026-01-29 | 2026-02-15 | 2026-02-20 | 2027-02-14 | 2027-08-31 | 6.6 | 18% |  | 198 | 6.6 | 562 | 18.7333
17 | S04 | 239 SQ YD | BRICKS | 2026-05-22 | 2026-06-15 | 2026-06-04 | 2027-04-30 | 2027-09-14 | 4.5667 | 2% |  | 137 | 4.5667 | 456 | 15.2
18 | S06 | 317 SQ YD | BRICKS | 2026-06-01 | 2026-06-15 | 2026-06-04 | 2027-06-30 | 2027-12-15 | 5.6 | 5% |  | 168 | 5.6 | 548 | 18.2667
19 | S10 | 216 SQ YD | VAIDEHI | 2026-02-25 | 2026-04-06 | 2026-05-17 | 2027-04-05 | 2027-07-31 | 3.9 | 5% |  | 117 | 3.9 | 481 | 16.0333
20 | S12A | 317 SQ YD | VAIDEHI | 2026-02-10 | 2026-05-06 | 2026-05-17 | 2027-08-05 | 2027-11-30 | 3.9 | 5% |  | 117 | 3.9 | 573 | 19.1
21 | S14 | 351 SQ YD | AVS | 2025-04-30 | 2025-06-06 | 2025-06-06 | 2026-06-05 | 2026-10-15 |  | 85% |  | 132 | 4.4 | 496 | 16.5333
22 | S18 | 163 SQ YD | AVS | 2025-01-24 | 2025-02-24 | 2025-05-15 | 2026-02-23 | 2026-09-30 |  | 90% | 96 | 219 | 7.3 | 583 | 19.4333
23 | S30 | 351 SQ YD | AVS | 2025-05-22 | 2025-06-15 | 2025-06-09 | 2026-06-14 | 2026-12-31 |  | 75% | 188 | 200 | 6.6667 | 564 | 18.8
24 | S34 | 492 SQ YD | BRICKS | 2026-03-11 | 2026-04-15 | 2026-05-02 | 2027-07-14 | 2027-07-31 | 0.56667 | 5% | 400 | 17 | 0.56667 | 472 | 15.7333
25 | S37 | 285 SQ YD | AVS | 2025-06-11 | 2025-06-24 | 2025-11-23 | 2026-06-23 | 2027-02-15 | 7.9 | 48% | 234 | 237 | 7.9 | 601 | 20.0333
26 | S38 | 239 SQ YD | BRICKS | 2026-03-16 | 2026-04-24 | 2026-05-13 | 2027-04-23 | 2027-05-31 | 1.2667 | 10% | 339 | 38 | 1.2667 | 402 | 13.4
27 | S40 | 163 SQ YD | BRICKS | 2026-03-16 | 2026-04-24 | 2026-05-13 | 2027-04-23 | 2027-06-30 | 2.2667 | 5% | 369 | 68 | 2.2667 | 432 | 14.4
28 | S50 | 317 SQ TD | AVS | 2025-09-20 | 2025-06-06 | 2025-05-15 | 2026-08-05 | 2027-02-15 | 6.4667 | 45% | 234 | 194 | 6.4667 | 619 | 20.6333
29 | S54 | 421 SQ YD | AVS | 2025-05-28 | 2026-01-21 | 2026-01-21 | 2027-01-20 | 2027-06-30 | 5.3667 | 25% | 369 | 161 | 5.3667 | 525 | 17.5
30 | S60 | 545 SQ YD | AVS | 2025-01-21 | 2025-02-24 | 2025-05-13 | 2026-02-23 | 2027-06-30 | 16.4 | 27% | 369 | 492 | 16.4 | 856 | 28.5333

## Villa delay status (hidden)
The Sage By Repose
| Villa Progress Report -22 JUN 2026 |  |  |  | Strt Date |  | Possession Date
Sr. No | Villa No. | Villa type (BHK) | Contractor Name | Customer Signature Date | Sign off | Actual | Sign off | Actual | Over all Work % | 2026-06-26 | Delay Days | Delay in Months | Actual time Taken Days | Actual time Taken Months
1 | N3A | 421 SQ YD | Real Infra | 2025-03-19 | 2025-04-06 | 2025-05-20 | 2026-04-05 | 2026-11-30 | 60% | 157 | 239 | 7.9667 | 603 | 20.1
2 | N05 | 216 SQ YD | Real Infra | 2025-01-22 | 2025-02-24 | 2025-04-15 | 2026-02-23 | 2026-08-31 | 92% | 66 | 189 | 6.3 | 553 | 18.4333
3 | N09 | 480 SQ YD | Real Infra | 2025-07-09 | 2025-08-24 | 2025-11-18 | 2026-08-23 | 2026-12-31 | 40% | 188 | 130 | 4.3333 | 494 | 16.4667
4 | N10 | 216 SQ YD | Real Infra | 2025-01-20 | 2025-02-15 | 2025-04-18 | 2026-02-14 | 2026-07-31 | 95% | 35 | 167 | 5.5667 | 531 | 17.7
5 | N12A | 216 SQ YD | Z Square | 2026-01-01 | 2026-02-20 | 2026-02-20 | 2027-02-19 | 2027-06-30 | 15% |  | 131 | 4.3667 | 495 | 16.5
6 | N14 | 216 SQ YD | Real infra | 2025-06-21 | 2025-07-24 | 2025-11-12 | 2026-07-23 | 2026-11-30 | 45% | 157 | 130 | 4.3333 | 494 | 16.4667
7 | N15 | 216 SQ YD | Nirvay Infra | 2026-02-21 | 2026-04-06 | 2026-05-21 | 2027-04-05 | 2027-07-31 | 5% |  | 117 | 3.9 | 481 | 16.0333
8 | N16 | 587 SQ YD | Nirvay Infra | 2026-03-31 | 2026-05-06 | 2026-05-21 | 2027-08-05 | 2027-11-30 | 5% |  | 117 | 3.9 | 573 | 19.1
9 | N22 | 480 SQ YD | Real Infra | 2025-07-29 | 2025-08-24 | 2025-11-17 | 2026-08-23 | 2027-02-28 | 38% | 247 | 189 | 6.3 | 553 | 18.4333
10 | N26 | 545 SQ YD | Real Infra | 2025-06-28 | 2025-08-15 | 2025-11-18 | 2026-08-14 | 2027-02-28 | 30% | 247 | 198 | 6.6 | 562 | 18.7333
11 | N27 | 216 SQ YD | Real Infra | 2025-04-22 | 2025-05-24 | 2025-05-20 | 2026-05-23 | 2026-10-30 | 60% | 126 | 160 | 5.3333 | 524 | 17.4667
12 | N29 | 216 SQ YD | Z Square | 2025-07-31 | 2025-09-06 | 2025-12-16 | 2026-09-05 | 2027-04-30 | 18% | 308 | 237 | 7.9 | 601 | 20.0333
13 | N36 | 317 SQ YD | Real Infra | 2025-05-23 | 2025-06-24 | 2025-11-11 | 2026-06-23 | 2027-02-28 | 38% | 247 | 250 | 8.3333 | 614 | 20.4667
14 | N62 | 216 SQ YD | Real Infra | 2025-02-06 | 2025-03-15 | 2025-04-17 | 2026-03-14 | 2026-08-11 | 80% | 46 | 150 | 5 | 514 | 17.1333
15 | N66 | 216 SQ YD | Z Square | 2025-10-27 | 2026-02-24 | 2026-02-20 | 2027-02-23 | 2027-06-30 | 15% |  | 127 | 4.2333 | 491 | 16.3667
16 | S02 | 494 SQ YD | BRICKS | 2026-01-29 | 2026-02-15 | 2026-02-20 | 2027-02-14 | 2027-08-31 | 18% |  | 198 | 6.6 | 562 | 18.7333
17 | S04 | 239 SQ YD | BRICKS | 2026-05-22 | 2026-06-15 | 2026-06-04 | 2027-04-30 | 2027-09-14 | 2% |  | 137 | 4.5667 | 456 | 15.2
18 | S06 | 317 SQ YD | BRICKS | 2026-06-01 | 2026-06-15 | 2026-06-04 | 2027-06-30 | 2027-12-15 | 5% |  | 168 | 5.6 | 548 | 18.2667
19 | S10 | 216 SQ YD | VAIDEHI | 2026-02-25 | 2026-04-06 | 2026-05-17 | 2027-04-05 | 2027-07-31 | 5% |  | 117 | 3.9 | 481 | 16.0333
20 | S12A | 317 SQ YD | VAIDEHI | 2026-02-10 | 2026-05-06 | 2026-05-17 | 2027-08-05 | 2027-11-30 | 5% |  | 117 | 3.9 | 573 | 19.1
21 | S14 | 351 SQ YD | AVS | 2025-04-30 | 2025-06-06 | 2025-06-06 | 2026-06-05 | 2026-10-15 | 85% |  | 132 | 4.4 | 496 | 16.5333
22 | S18 | 163 SQ YD | AVS | 2025-01-24 | 2025-02-24 | 2025-05-15 | 2026-02-23 | 2026-09-30 | 90% | 96 | 219 | 7.3 | 583 | 19.4333
23 | S30 | 351 SQ YD | AVS | 2025-05-22 | 2025-06-15 | 2025-06-09 | 2026-06-14 | 2026-12-31 | 75% | 188 | 200 | 6.6667 | 564 | 18.8
24 | S34 | 492 SQ YD | BRICKS | 2026-03-11 | 2026-04-15 | 2026-05-02 | 2027-07-14 | 2027-07-31 | 5% | 400 | 17 | 0.56667 | 472 | 15.7333
25 | S37 | 285 SQ YD | AVS | 2025-06-11 | 2025-06-24 | 2025-11-23 | 2026-06-23 | 2027-02-15 | 48% | 234 | 237 | 7.9 | 601 | 20.0333
26 | S38 | 239 SQ YD | BRICKS | 2026-03-16 | 2026-04-24 | 2026-05-13 | 2027-04-23 | 2027-05-31 | 10% | 339 | 38 | 1.2667 | 402 | 13.4
27 | S40 | 163 SQ YD | BRICKS | 2026-03-16 | 2026-04-24 | 2026-05-13 | 2027-04-23 | 2027-06-30 | 5% | 369 | 68 | 2.2667 | 432 | 14.4
28 | S50 | 317 SQ TD | AVS | 2025-09-20 | 2025-06-06 | 2025-05-15 | 2026-08-05 | 2027-02-15 | 45% | 234 | 194 | 6.4667 | 619 | 20.6333
29 | S54 | 421 SQ YD | AVS | 2025-05-28 | 2026-01-21 | 2026-01-21 | 2027-01-20 | 2027-06-30 | 25% | 369 | 161 | 5.3667 | 525 | 17.5
30 | S60 | 545 SQ YD | AVS | 2025-01-21 | 2025-02-24 | 2025-05-13 | 2026-02-23 | 2027-06-30 | 27% | 369 | 492 | 16.4 | 856 | 28.5333