## Sheet1
PROJECT: THE SAGE BY REPOSE — CONSTRUCTION PLANNING
START DATE: Oct 2024 ¦ END DATE: DEC 2027 ¦ PROJECT DURATION: ~3 Years
[6 empty] | MONTHS PASSED(31ST MAY,26) | ACTUAL (%) COMPLETE
TASK NO. | TASK NAME | START DATE | PLANNED END DATE | END DATE | DURATION(in days) |  |  | #REF!
1 | MAIN GATE(INC. STRUCTURE) | NA | Completed |  | 0 |  | 100%
2 | MATERIAL GATE | NA | Completed |  | 0 |  | 100%
3 | PLOT BOUNDRY WALL | NA | Completed |  | 0 |  | 100%
1.0 SOUTH GREENWAY-1 | [6 empty] | 100%
1.1 | Civil work | 11-Dec-24 | Completed |  | 0 |  | 100%
1.2 | MEP work | 08-Jan-25 | Completed |  | 0 |  | 100%
1.3 | Finishing Work | 20-Jan-25 | Completed |  | 0 |  | 100%
1.4 | lighting work | 20-Jan-25 | Completed |  | 0 |  | 100%
1.5 | Landscape work | 25-Jan-25 | Completed |  | 0 |  | 100%
2.0 SOUTH GREENWAY -2 |  |  |  |  | 10MONTHS | 3.53 | 60%
2.1 | Civil work | 2026-02-15 | 2026-05-15 | 2026-09-30 | 227 |  | 80%
2.2 | MEP work(PRE) | 2026-06-15 | 2026-10-31 | 2026-06-25 | 10 |  | 100%
2.3 | Finishing Work | 2026-06-16 | 2026-10-31 | 2026-11-30 | 167 |  | 0%
| MEP Work(post) | 2026-11-13 |  | 2026-11-30 | 17 |  | 0%
2.4 | lighting work | 2026-10-30 | 2026-10-15 | 2026-11-30 | 31 |  | 0%
2.5 | Landscape work | 2026-11-15 | 2026-10-31 | 2027-01-15 | 61 |  | 0%
3.0 SOUTH GREENWAY-3 |  |  |  |  | 10MONTHS | 3.13 | 33.33%
3.1 | Civil work | 2026-02-27 | 2026-05-30 | 2026-09-30 | 215 |  | 60%
3.2 | MEP work(PRE) | 2026-06-30 | 2026-10-31 | 2026-07-10 | 10 |  | 40%
3.3 | Finishing Work | 2026-07-01 | 2026-10-31 | 2026-12-15 | 167 |  | 0%
| MEP Work(post) | 2026-12-01 |  | 2026-12-11 | 10 |  | 0%
3.4 | lighting work | 2026-11-15 | 2026-10-15 | 2026-12-15 | 30 |  | 0%
3.5 | Landscape work | 2026-09-25 | 2026-10-31 | 2026-11-25 | 61 |  | 0%
4.0 SOUTH GREENWAY-4 |  |  |  |  | 11MONTHS | 3.53 | 36.67%
4.1 | Civil work | 2026-02-15 | 2026-06-30 | 2026-09-30 | 227 |  | 60%
4.2 | MEP work(PRE) | 2026-07-15 | 2026-12-31 | 2026-07-25 | 10 |  | 50%
4.3 | Finishing Work | 2026-06-30 | 2026-12-31 | 2026-12-31 | 184 |  | 0%
| MEP Work(post) | 2026-11-20 |  | 2026-11-30 | 10 |  | 0%
4.4 | lighting work | 2026-11-15 | 2026-10-15 | 2026-12-15 | 30 |  | 0%
4.5 | Landscape work | 2026-09-25 | 2026-10-31 | 2026-11-25 | 61 |  | 0%
5.0 SOUTH GREENWAY-5 |  |  |  |  | 10MONTHS | 0.9 | 16.67%
5.1 | Civil work | 2026-05-05 | 2026-09-05 | 2026-10-15 | 163 |  | 50%
5.2 | MEP work(PRE) | 2026-07-15 | 2026-12-31 | 2026-07-25 | 10 |  | 0%
5.3 | Finishing Work | 2026-08-20 | 2026-12-31 | 2027-01-31 | 164 |  | 0%
| MEP Work(post) | 2026-12-31 |  | 2027-01-10 | 10 |  | 0%
5.4 | lighting work | 2027-01-01 | 2026-12-15 | 2027-01-31 | 30 |  | 0%
5.5 | Landscape work | 2026-11-15 | 2026-12-31 | 2027-01-15 | 61 |  | 0%
6.0 NORTH GREENWAY-1 |  |  |  |  | 12MONTHS | 7.63 | 76.67%
6.1 | Civil work | 2025-10-15 | 2026-02-28 | 2026-07-31 | 289 |  | 90%
6.2 | MEP work(PRE) | 2026-04-01 | 2026-08-15 | 2026-04-11 | 10 |  | 70%
6.3 | Finishing Work | 2026-04-20 | 2026-08-15 | 2026-09-30 | 163 |  | 40%
| MEP Work(post) | 2026-09-15 |  | 2026-09-25 | 10 |  | 0%
6.4 | lighting work | 2026-08-30 | 2026-07-30 | 2026-09-30 | 31 |  | 0%
6.5 | Landscape work | 2026-07-11 | 2026-08-15 | 2026-09-10 | 61 |  | 30%
7.0 NORTH GREENWAY-2 |  |  |  |  | 8MONTHS | 0.03 | 6.667%
7.1 | Civil work | 2026-05-31 | 2026-08-31 | 2026-10-30 | 152 |  | 20%
7.2 | MEP work(PRE) | 2026-08-01 | 2026-12-31 | 2026-08-11 | 10 |  | 0%
7.3 | Finishing Work | 2026-07-15 | 2026-12-31 | 2026-12-31 | 169 |  | 0%
| MEP Work(post) | 2026-12-15 |  | 2026-12-25 | 10 |  | 0%
7.4 | lighting work | 2026-12-01 | 2026-12-15 | 2026-12-31 | 30 |  | 0%
7.5 | Landscape work | 2026-10-10 | 2026-12-31 | 2026-12-10 | 61 |  | 0%
8.0 NORTH GREENWAY-3 |  |  |  |  | 6MONTHS | -3.53 | 0%
8.1 | Civil work | 2026-09-15 | 2027-01-15 | 2027-01-15 | 122 |  | 0%
8.2 | MEP work(PRE) | 2026-12-01 | 2027-01-10 | 2026-12-11 | 10 |  | 0%
8.3 | Finishing Work | 2026-11-15 | 2026-12-31 | 2027-04-24 | 160 |  | 0%
| MEP Work(post) | 2027-04-10 |  | 2027-04-20 | 10 |  | 0%
8.4 | lighting work | 2027-04-01 | 2026-12-15 | 2027-05-01 | 30 |  | 0%
8.5 | Landscape work | 2026-10-31 | 2027-02-28 | 2027-03-16 | 136 |  | 0%
9.0 NORTH GREENWAY-4 |  |  |  |  | 6MONTHS | -4.07 | 0%
9.1 | Civil work | 2026-10-01 | 2027-01-31 | 2027-01-31 | 122 |  | 0%
9.2 | MEP work(PRE) | 2026-12-16 | 2026-12-31 | 2026-12-26 | 10 |  | 0%
9.3 | Finishing Work | 2026-11-01 | 2026-12-31 | 2027-04-10 | 160 |  | 0%
| MEP Work(post) | 2027-03-25 |  | 2027-04-04 | 10 |  | 0%
9.4 | lighting work | 2026-11-14 | 2026-12-15 | 2026-12-15 | 31 |  | 0%
9.5 | Landscape work | 2026-10-31 | 2027-03-18 | 2027-03-18 | 138 |  | 0%
10.0 NORTH GREENWAY-5 |  |  |  |  | 8MONTHS | 0.57 | 13.33%
10.1 | Civil work | 2026-05-15 | 2026-08-30 | 2026-10-10 | 148 |  | 40%
10.2 | MEP work(PRE) | 2026-07-30 | 2026-12-31 | 2026-08-10 | 11 |  | 0%
10.3 | Finishing Work | 2026-07-20 | 2026-12-31 | 2026-12-30 | 163 |  | 0%
| MEP Work(post) | 2026-10-20 |  | 2026-10-30 | 10 |  | 0%
10.4 | lighting work | 2026-11-30 | 2026-12-15 | 2026-12-30 | 30 |  | 0%
10.5 | Landscape work | 2026-10-10 | 2026-12-31 | 2026-12-10 | 61 |  | 0%
11.0 RECREATION LOUNGE |  |  |  |  | 27MONTHS | 20.13 | 30%
11.1 | Civil work | 2024-10-05 | 2026-09-15 | 2026-09-15 | 710 |  | 70%
11.2 | MEP work | 2026-06-16 | 2026-12-31 | 2026-11-30 | 167 |  | 20%
11.3 | Finishing work | 2026-08-01 | 2026-12-31 | 2026-12-15 | 136 |  | 0%
11.4 | Interior Work | 2026-10-16 | 2026-12-31 | 2027-01-15 | 91 |  | 0%
11.5 | Landscape work | 2026-07-16 | 2026-12-31 | 2026-10-15 | 91 |  | 0%
11.6 | lighting work | 2026-11-16 | 2026-12-31 | 2027-01-15 | 60 |  | 0%
12.0 CLUB HOUSE |  |  |  |  | 23MONTHS | 3.53 | 10%
12.1 | Civil work | 2026-02-15 | 2026-11-29 | 2026-11-29 | 287 |  | 30%
12.2 | MEP work | 2026-08-01 | 2027-12-15 | 2027-12-15 | 501 |  | 0%
12.3 | Finishing work | 2026-12-01 | 2027-12-31 | 2027-12-31 | 395 |  | 0%
12.4 | Interior Work | 2027-07-01 | 2027-12-31 | 2027-12-31 | 183 |  | 0%
12.5 | Landscape work | 2027-10-01 | 2027-12-31 | 2027-12-31 | 91 |  | 0%
12.6 | lighting work | 2027-10-01 | 2027-12-15 | 2027-12-15 | 75 |  | 0%
13 | COMMON AREA LANDSCAPING DEVELOPMENT | 2024-12-15 | 2026-11-30 | 2026-11-30 | 24MONTHS | 17.77 | 70%
14 | PLUMBING WORKS & IRRIGATION WORK | 2026-02-24 | 2026-10-30 | 2026-10-30 | 9MONTHS | 3.23 | 90%
15 | ELECTRIC WORKS | 2026-04-24 | 2026-12-30 | 2026-12-30 | 9MONTHS | 1.27 | 50%
16 | INTERNAL ROADS WITH TRIMIX | 2025-02-06 | 2027-12-31 | 2027-12-31 | 36MONTHS | 16 | 50%

## Sheet2
2026-08-30
| Wings | Start Date |  | Possession Date |  | Actual time to delivery (months) | Over all Work % as on date |  | Time to delivery (months) | Status | Delayed % | Delayed In Months
|  | Committed | Actual | Committed | Actual |  | Committed | Actual
North Zone
1 | N10 | 2025-02-15 | 2025-04-18 | 2026-02-14 | 2026-07-31 | 15.6333 | 100% | 95% | -1 | Delayed | 5% | 0.78167
2 | N62 | 2025-03-15 | 2025-04-17 | 2026-03-14 | 2026-10-11 | 18.0667 | 100% | 85% | 1.4 | Delayed | 15% | 2.71
3 | N05 | 2025-02-24 | 2025-04-15 | 2026-02-23 | 2026-08-31 | 16.7667 | 100% | 92% | 0.033333 | Delayed | 8% | 1.3413
4 | N27 | 2025-05-24 | 2025-05-20 | 2026-05-23 | 2026-10-30 | 17.6 | 100% | 60% | 2.0333 | Delayed | 40% | 7.04
5 | N14 | 2025-07-24 | 2025-11-12 | 2026-07-23 | 2026-11-30 | 12.7667 | 100% | 50% | 3.0667 | Delayed | 50% | 6.3833
6 | N3A | 2025-04-06 | 2025-05-20 | 2026-04-05 | 2026-11-30 | 18.6333 | 100% | 60% | 3.0667 | Delayed | 40% | 7.4533
7 | N09 | 2025-08-24 | 2025-11-18 | 2026-08-23 | 2026-12-31 | 13.6 | 95% | 45% | 4.1 | Delayed | 50% | 6.8
8 | N22 | 2025-08-24 | 2025-11-17 | 2026-08-23 | 2027-02-28 | 15.6 | 95% | 40% | 6.0667 | Delayed | 55% | 8.58
9 | N26 | 2025-08-15 | 2025-11-18 | 2026-08-14 | 2027-02-28 | 15.5667 | 95% | 35% | 6.0667 | Delayed | 60% | 9.34
10 | N36 | 2025-06-24 | 2025-11-11 | 2026-06-23 | 2027-02-28 | 15.8 | 100% | 38% | 6.0667 | Delayed | 62% | 9.796
11 | N29 | 2025-09-06 | 2025-12-16 | 2026-09-05 | 2027-04-30 | 16.6667 | 90% | 30% | 8.1 | Delayed | 60% | 10
12 | N66 | 2026-02-24 | 2026-02-20 | 2027-02-23 | 2027-06-30 | 16.5 | 40% | 20% | 10.1333 | Delayed | 20% | 3.3
13 | N12A | 2026-02-20 | 2026-02-20 | 2027-02-19 | 2027-06-30 | 16.5 | 40% | 15% | 10.1333 | Delayed | 25% | 4.125
14 | N15 | 2026-04-06 | 2026-05-21 | 2027-04-05 | 2027-07-31 | 14.5333 |  | 15% | 11.1667 | In Progress
15 | N16 | 2026-05-06 | 2026-05-21 | 2027-08-05 | 2027-10-31 | 17.6 |  | 15% | 14.2333 | In Progress
16 | N64 | 2026-09-30 |  | 2028-03-30 | [5 empty] | Not Started
17 | N53 | 2026-09-30 |  | 2028-03-30 | [5 empty] | Not Started
18 | N 6/78 | 2026-09-15 |  | 2027-12-14 | [5 empty] | Not Started
19 | N11 | 2026-09-15 |  | 2028-03-14 | [5 empty] | Not Started
South Zone
1 | S18 | 2025-02-24 | 2025-05-15 | 2026-02-23 | 2026-09-30 | 16.7667 | 100% | 90% | 1.0333 | Delayed | 10% | 1.6767
2 | S14 | 2025-06-06 | 2025-06-06 | 2026-06-05 | 2026-10-15 | 16.5333 | 100% | 85% | 1.5333 | Delayed | 15% | 2.48
3 | S30 | 2025-06-15 | 2025-06-09 | 2026-06-14 | 2026-12-31 | 19 | 100% | 75% | 4.1 | Delayed | 25% | 4.75
4 | S37 | 2025-06-24 | 2025-11-23 | 2026-06-23 | 2027-02-15 | 14.9667 | 100% | 50% | 5.6333 | Delayed | 50% | 7.4833
5 | S50 | 2025-06-06 | 2025-05-15 | 2026-08-05 | 2027-03-31 | 22.8333 | 100% | 60% | 7.1 | Delayed | 40% | 9.1333
6 | S40 | 2026-04-24 | 2026-05-13 | 2027-04-23 | 2027-05-31 | 12.7667 |  | 20% | 9.1333 | In Progress
7 | S38 | 2026-04-24 | 2026-05-13 | 2027-04-23 | 2027-06-30 | 13.7667 |  | 20% | 10.1333 | In Progress
8 | S54 | 2026-01-21 | 2026-01-21 | 2027-01-20 | 2027-06-30 | 17.5 | 50% | 30% | 10.1333 | Delayed | 20% | 3.5
9 | S60 | 2025-02-24 | 2025-05-13 | 2026-02-23 | 2027-06-30 | 25.9333 | 100% | 40% | 10.1333 | Delayed | 60% | 15.56
10 | S34 | 2026-04-15 | 2026-05-02 | 2027-07-14 | 2027-07-31 | 15.1667 |  | 20% | 11.1667 | In Progress
11 | S10 | 2026-04-06 | 2026-05-17 | 2027-04-05 | 2027-07-31 | 14.6667 |  | 5% | 11.1667 | In Progress
12 | S02 | 2026-02-15 | 2026-02-20 | 2027-02-14 | 2027-07-31 | 17.5333 |  | 20% | 11.1667 | In Progress
13 | S04 | 2026-06-15 | 2026-06-04 | 2027-04-30 | 2027-08-14 | 14.5333 |  | 5% | 11.6333 | In Progress
14 | S12A | 2026-05-06 | 2026-05-17 | 2027-08-05 | 2027-10-31 | 17.7333 |  | 5% | 14.2333 | In Progress
15 | S06 | 2026-06-15 | 2026-06-04 | 2027-06-30 | 2027-11-15 | 17.6333 |  | 10% | 14.7333 | In Progress
16 | S 07/08 | 2026-09-30 |  | 2028-03-30 | [5 empty] | Not Started
17 | S32 | 2026-09-15 |  | 2027-12-14 | [5 empty] | Not Started
[7 empty] | 90.25% | 41% | 217.7 |  | 49.25%
| Zones | North Zone | South Zone | Recration Lounge | Club House | ROADS |  | Common Area Landscaping Work Development
| Wings | 1.Villas | Villas
|  | 2.Green Ways | Green Ways
| floors | Villas
|  | N10 | S18 | Civil work | Civil work
|  | N62 | S14 | Landscape work | Landscape work
|  | N05 | S30 | Finishing work | Finishing work
|  | N27 | S37 | MEP work | MEP work
|  | N14 | S50
|  | N3A | S40
|  | N09 | S38
|  | N22 | S54
|  | N26 | S60
|  | N36 | S34
|  | N29 | S10
|  | N66 | S02
|  | N12A | S04
|  | N15 | S12A
|  | N16 | S06
|  | N64 | S 07/08
|  | N53 | S32
N 6/78
N11
GreenWays
|  | North Green way 1 | South Green Way 1
|  | North Green way 2 | South Green Way 2
|  | North Green way 3 | South Green Way 3
|  | North Green way 4 | South Green Way 4
|  | North Green way 5 | South Green Way 5